## RC Received & Spent
S.No | Date | Received From | Amount | Total |  | Date | Spent on | Amount | COMMENTS
1 |  | Azeem - From Ammi | 70000 | 70000 | -5225576 | 20-12-2014 | Amount Spent on RC Till 20-12-2014
1 |  | Azeem | 300000 | 1826000 |  |  | From this Amount we have Completed the Following works for four floors : 1. Complete STRUCTURE 2. Complete Brick WORK 3. Complete Plastering 4. Complete Gowa opened 5. Complete Electrical Fitting 6. Water Proofing in 20 Bathrooms 7. Plumbing Work Piping 8. Exterior Putty & Premier 9. Fourr floors Luppum & 3 Flrs Paint 10. Balcony Railing & Glass Work 11. | 16521576 | 1. I hope Electrical Work Will be finished in next 2 weeeks 2. Elevation & outer Plastering will take another 2 or 3 weeks, WE have enough cement but no sand 3. Inshallah nex week I will purchase CPVC internal fitting Then will star pluming internal work also.
2 |  | Azeem | 164000
3 |  | Azeem - Acc Transfer | 400000
4 |  | Azeem - Acc Transfer | 300000
5 |  | Azeem - Acc Transfer | 500000
6 |  | Azeem - Acc Transfer | 100000
7 |  | Azeem - ATM With Draw | 40000
8 |  | Azeem - Brick & Iftaar | 22000
1 |  | From Arshad Client 101 | 300000 | 4325000
2 |  | From Arshad Client 101 | 1200000
3 |  | From Arshad Client 101 | 900000
4 |  | From Arshad Client 101 | 900000
5 | 2015-05-30 | From Arshad Client 101 | 875000
6 |  | From Arshad Client 101 Additional | 150000
1 | 2015-10-22 | From Client - 301 Shahensha | 500000 | 4575000
2 | 2015-11-04 | From Client - 301 Shahensha | 600000
3 | 2015-12-04 | From Client - 301 Shahensha | 600000
4 | 2015-12-12 | From Client - 301 Shahensha | 400000
5 | 2016-01-05 | From Client - 301 Shahensha | 1000000
6 | 2016-01-16 | From Client - 301 Shahensha | 1475000
1 |  | From Bhayya for Flat # 201 | 500000 | 500000
1 |  | From Farooq Bh | 100000 | 0
2 |  | Paid back to Farooq Bh | -100000
1 |  | From Bhayya - Personal Loan | 500000 | 0
2 | 8-Arp-2015 | From Bhayya - Personal Loan - Paid Back | -500000
3 | 2016-02-01 | Unknowingly Personal Loan 10,00,000 |  |  |  | Amount Spent on RC by Kaleem |  | 16521576
From Saber - 3,00,000
Amount Received by Kaleem |  |  | 11296000

## Sheet1
Row Labels | Sum of Amount
Aminities - Designing | 102200
Aminities - Borewell | 222250
Aminities - Documentation | 27400
Aminities - Electrical Dept | 373550
Aminities - Elevation | 118100
Aminities - Fabrication | 190300
Aminities - Gen | 9000
Aminities - GHMC | 788500
Aminities - Gowa | 157020
Aminities - Lift | 398500
Aminities - Marble | 64500
Aminities - Parking Flooring | 156960
Aminities - Water Dept | 288300
Brick | 908170
Cement | 1271055
Centering | 958600
Chipping | 57400
Electrical Material | 509360
Electrition | 152000
Excavation | 347470
Fabrication | 67500
Fabrication - Flats | 80500
False Ceiling | 97500
Flooring - Lifting | 25500
flooring - Marble | 54750
Granite | 72100
Granite Fixer | 51000
Kankar | 265600
Marble | 58000
Mason - Brick | 1563900
Mason - Concrete | 280200
Mason - Dept | 27300
Mason - Lift | 21900
MISC | 316214
Paint Material | 21040
Painter | 283000
Painter Material | 153410
Personal | 0
Plumber | 139000
Plumber | 26000
Plumbing Material | 301112
Polish | 23000
Sand | 1167370
Sanitory | 255416
Steel | 2076350
Tiles | 362300
Tiles Fixer | 107300
UPVC | 314000
Utilities | 205169
UVI | 282080
Water Proofing | 54600
Wood | 667830
Grand Total | 16521576

## Daily Entries
S.No | Date | Particulars | Amount | Work Type | Comments | Receipt Attachment
1 | 2013-08-07 | Shafi Sahab - floor Plan | 30000 | Aminities - Designing |  |  | 1 | Aminities - Designing
2 | 2013-08-07 | Dayanand - GHMC | 25000 | Aminities - GHMC |  |  | 2 | Aminities - Borewell
3 | 17-7-2013 | HMWS + SB DD - Water | 150000 | Aminities - Water Dept |  |  | 3 | Aminities - Documentation
4 | 17-7-2013 | Raheem Saab - Water | 15000 | Aminities - Water Dept |  |  | 4 | Aminities - Electrical Dept
5 | 21-7-2013 | Raheem Saab - Water | 15000 | Aminities - Water Dept |  |  | 5 | Aminities - Elevation
6 | 24-7-2013 | Raheem Saab - Water | 3000 | Aminities - Water Dept |  |  | 6 | Aminities - Fabrication
7 |  | Dayanand - GHMC - Plan Revised | 5000 | Aminities - GHMC |  |  | 7 | Aminities - Gen
8 | 2013-08-07 | Anwar Bhai - Floor Plan | 4000 | Aminities - Designing |  |  | 8 | Aminities - GHMC
9 | 2013-01-08 | GHMC - DD | 10000 | Aminities - GHMC |  |  | 9 | Aminities - Gowa
10 | 22/8/2013 | GHMC - Brb | 125000 | Aminities - GHMC |  |  | 10 | Aminities - Granite
11 | 21-8-2013 | Anwar Bhai - Floor Plan | 6000 | Aminities - Designing |  |  | 11 | Aminities - Lift
12 | 29-8-2014 | UVI - Firm Registration | 1000 | UVI |  |  | 12 | Aminities - Marble
13 |  | NSC | 5000 | UVI |  |  | 13 | Aminities - Parking Flooring
14 | 17-9-2013 | UVI - Visiting Cards | 1000 | UVI |  |  | 14 | Aminities - Water Dept
15 | 2013-06-09 | Khaled | 2200 | Aminities - Designing |  |  | 15 | Brick
16 |  | Plot Cleaning | 2200 | Excavation |  |  | 16 | Cement
17 |  | ZR Associates | 1500 | Aminities - Documentation |  |  | 17 | Centering
18 |  | Builder License | 15000 | Aminities - Documentation |  |  | 18 | Chipping
19 |  | Firm Registration Agreement | 2100 | UVI |  |  | 19 | Electrical Material
20 |  | Brochure Adv | 3000 | UVI |  |  | 20 | Electrition
21 |  | Brochure Payment | 15000 | UVI |  |  | 21 | Excavation
22 |  | Brochure Payment | 5000 | UVI |  |  | 22 | Fabrication - Flats
23 |  | Taufeeq Arch | 26000 | Aminities - Designing |  |  | 23 | False Ceiling
24 |  | Land Surveyor | 2500 | Excavation |  |  | 24 | Flooring - Lifting
25 |  | ZR Associates - (Mortigage) | 7100 | Aminities - Documentation |  |  | 25 | Flooring - Marble
26 |  | ZR Associates - (Services) | 2000 | Aminities - Documentation |  |  | 26 | Granite
27 |  | Borewell - Digging | 107950 | Aminities - Borewell |  |  | 27 | Granite Fixer
28 |  | Land Surveyor | 2500 | Excavation |  |  | 28 | Kankar
29 |  | Paul - Excavation | 155000 | Excavation |  |  | 29 | Marble
30 |  | Material for Footing Marking | 670 | Excavation |  |  | 30 | Mason - Brick
31 |  | Paul | 120000 | Excavation |  |  | 31 | Mason - Concrete
32 |  | Plot Cleaning - Neighbours | 30000 | Excavation |  |  | 32 | Mason - Dept
33 |  | Drilling - Footing | 7300 | Excavation |  |  | 33 | Mason - Lift
34 |  | Pits Leveling | 15500 | Excavation |  |  | 34 | MISC
35 |  | Ganet | 4200 | Excavation |  |  | 35 | Paint Material
36 |  | Ganet Moving | 1600 | Excavation |  |  | 36 | Painter
37 |  | Steel for Footing | 40000 | Steel |  |  | 38 | Personal
38 |  | Centering - Adv | 15000 | Centering |  |  | 39 | Plumber
39 |  | Mason - Marking | 5000 | Mason - Brick |  |  | 40 | Plumbing Material
40 |  | Meter DD | 10050 | Aminities - Electrical Dept |  |  | 41 | Polish
41 |  | Meter Bribe | 7500 | Aminities - Electrical Dept |  |  | 42 | Sand
42 |  | Meter Fitting & Box | 1000 | Aminities - Electrical Dept |  |  | 43 | Sanitory
43 |  | Electrition - Waheed Bh | 800 | MISC |  |  | 44 | Steel
44 |  | Watchman (Chand Pasha) | 500 | Utilities |  |  | 45 | Tiles
45 |  | Watchman (Timmayya) | 200 | Utilities |  |  | 46 | Tiles Fixer
46 |  | Muggu Doori & Paint | 2500 | Excavation |  |  | 47 | UPVC
47 |  | Kankar | 7500 | Kankar |  |  | 48 | Utilities
48 |  | Mason - Basement Wall | 7500 | Mason - Brick |  |  | 49 | UVI
49 |  | Bending Wire 25 KG @ 63 | 1575 | Steel |  |  | 50 | Water Proofing
50 |  | Borewell Pump | 101000 | Aminities - Borewell |  |  | 51 | Wood
51 |  | Plastic Box for Meter & Motor Box | 650 | MISC |  |  | 37
52 |  | Gampay | 450 | MISC
53 |  | Naqul | 1800 | Excavation
54 |  | Kankar & Robo sand | 29000 | Sand
55 |  | Brick | 27500 | Brick
56 |  | Centering | 15000 | Centering
57 |  | Centering for rods inserting | 1200 | Centering
58 |  | Sand | 42240 | Sand
59 |  | Steel | 95000 | Steel
60 |  | Cement 100 Bags @ 197 | 19700 | Cement
61 |  | Cement 200 Bags @ 297 | 59400 | Cement
62 |  | Labour for Dismentaling | 1500 | MISC
63 |  | Dimmis | 450 | MISC
64 |  | GHMC DD | 300000 | Aminities - GHMC
65 |  | Nageshwar Rao | 5000 | Mason - Brick
66 |  | Metro | 10000 | Aminities - Designing
67 |  | Metro | 15000 | Aminities - Designing
68 |  | Dismentaling Leveling | 2300 | MISC
69 |  | Sand + Weight | 41800 | Sand
70 |  | Mason | 10000 | Mason - Brick
71 |  | Kankar | 7000 | Kankar
72 |  | Steel 20 MM | 2760 | Steel
73 |  | MISC Exp | 1000 | MISC
74 |  | Dismentaling | 2000 | MISC
75 |  | Centering | 20000 | Centering
76 |  | Bending Wire | 630 | MISC
77 |  | Cement & Steel for Columns | 50000 | Steel
78 |  | Centering Payment | 40000 | Centering
79 |  | Mason Pay | 15000 | Mason - Brick
80 |  | Brick | 27500 | Brick
81 |  | Material Dumping | 3000 | Aminities - GHMC
82 | 2014-01-08 | Elec Bill | 1200 | Utilities
83 | 2014-01-08 | 20 MM Kankar | 6600 | Kankar
84 | 2014-02-08 | EC, Xerox & Lamination | 1045 | MISC
85 | 2014-03-08 | Ballies, Bamboos, Line dori & Auto | 3000 | MISC
86 | 2014-02-08 | Supervisor Salary | 9000 | UVI
87 | 2014-03-08 | Centering Payment | 10000 | Centering
88 | 2014-04-08 | 99 Acres | 20000 | UVI
89 | 2014-04-08 | Sign Boards | 5650 | UVI
90 | 2014-05-08 | 1st Slab & Columns Steel | 179000 | Steel
91 | 2014-05-08 | Auto, Labour + Kaanta for steel | 2000 | Steel
92 | 2014-05-08 | Bamboos | 750 | MISC
93 | 2014-04-08 | G I Wire & Player | 350 | MISC
94 | 2014-07-08 | 1st Slab Kankar | 7000 | Kankar
95 | 2014-07-08 | 1st Slab Electricals | 10655 | Electrical Material
96 | 2014-07-08 | 1st Slab Cement 200 Bags @ 290 + Labour | 58600 | Cement
97 | 2014-07-08 | 8mm 60 Rods for 1st Slab | 12700 | Steel
98 | 2014-07-08 | 40 MM Kankar Moved from HH | 7000 | Kankar
99 | 2014-07-08 | Supervisor Salary - Adv | 5000 | UVI
100 | 2014-07-08 | Covering Blocks | 500 | MISC
101 | 2014-01-08 | Watchman Salary | 5500 | Utilities
102 | 2014-09-08 | Nageshwar Rao - 1st Slab Concrete | 35000 | Mason - Concrete
103 | 2014-09-08 | Sand | 46200 | Sand
104 | 2014-09-08 | Cement 100 Bags @ 293 | 29300 | Cement
105 | 2014-09-08 | Centering Payment | 60000 | Centering
106 | 2014-09-08 | Steel - Rings from Centering Guys | 8500 | Steel
107 | 2014-11-08 | Steel For Coloumns | 39000 | Steel
108 | 2014-11-08 | Electrition Work Payment for 1st Slab | 3000 | Electrition
109 | 2014-11-08 | Kankar | 14000 | Kankar
110 | 2014-11-08 | Centering Payment for 1st Slab | 40000 | Centering
111 | 13-8-2014 | Reddy Payment | 50000 | Steel
112 | 16-8-2014 | Curtain & Stopper | 4400 | UVI
113 | 15-8-2014 | Bedwork Labour | 4400 | MISC
114 | 15-8-2014 | Beam Telecom | 3800 | UVI
115 | 18-8-2014 | Centering Payment for Second Slab Coloumns | 20000 | Centering
116 | 18-8-2014 | Nageshwar Payment for Second Slab Coloumns - Concrete | 15000 | Mason - Concrete
117 | 20-8-2014 | Elec Bill | 2963 | Utilities
118 | 20-8-2014 | Xerox | 1350 | MISC
119 | 20-8-2014 | Bending Wire 5 Kg | 300 | Steel
120 | 25-8-2014 | Steel for Second Slab | 162000 | Steel
121 | 25-8-2014 | Oil For Second Slab | 600 | MISC
122 | 28-8-2014 | Cement 300 Bags @ 293 for Second Slab | 88000 | Cement
123 | 31-8-2014 | Sand for 1st Slab | 48800 | Sand
124 | 31-8-2014 | Kankar for Secnd Slab | 23000 | Kankar
125 | 26-8-2014 | Centering | 20000 | Centering
126 | 27-8-2014 | Nageshwar Adv for Bick Work | 100000 | Mason - Brick
127 | 27-8-2014 | Centering Inaam | 2400 | MISC
128 | 27-8-2014 | Door Frames Adv | 25000 | Wood
129 | 27-8-2014 | Covering Blocks for Second Slab | 900 | MISC
130 | 28-8-2014 | Kankar Adv for 4 Gadis | 5000 | Kankar
131 | 28-8-2014 | 8MM Steel 10 Kattay | 30600 | Steel
132 | 28-8-2014 | Supervisor Salary | 6200 | UVI
133 | 28-8-2014 | Second Slab Electricals | 5255 | Electrical Material
134 | 30-8-2014 | Bending Wire | 1750 | Steel
135 | 31-8-2014 | Second Slab Concrete Payment | 20000 | Mason - Concrete
136 | 31-8-2014 | Second Slab Concrete Payment Inaam | 350 | MISC
137 | 31-8-2014 | Second Slab Centering Payment | 40000 | Centering
138 | 31-8-2014 | Second Slab Centering Payment Inaam | 1000 | MISC
139 | 2014-02-09 | Watchman Salary + Inaam | 6000 | Utilities
140 | 2014-02-09 | Concreting Pin | 12000 | MISC
141 | 2014-03-09 | Cement 500 Bags @ 293 for 3rd & 4Th Slab | 145000 | Cement
142 | 2014-03-09 | Website Domain Renewal & Design | 10000 | UVI
143 | 2014-06-09 | Concrete Adv | 40000 | Mason - Concrete
144 | 31-9-2014 | Tarpaulin for slab on slab Day | 1750 | MISC
145 | 26-9-2014 | Bending Wire | 650 | Steel
146 | 2014-05-09 | Reddy Payment | 10000 | Steel
147 | 2014-05-09 | Borewell Pipe Fitting | 400 | MISC
148 | 2014-07-09 | Centering Payment for 3rd Slab Coloumns | 20000 | Centering
149 | 2014-09-09 | Concrete Payment for 3rd Slab Coloumns | 10000 | Mason - Concrete
150 | 2014-09-09 | Second Slab Electrition Payment | 4000 | Electrition
151 | 2014-09-09 | Centering Payment for 3rd Slab | 10000 | Centering
152 | 2014-11-09 | Sand for 3rd Slan 54 Tons @ 1000 | 54350 | Sand
153 | 2014-01-09 | Door Frames Payment | 134100 | Wood
154 | 2014-12-09 | Taanchay for First Slab | 2500 | Chipping
155 | 2014-12-09 | Taanchay for second Slab | 1800 | Chipping
156 | 13-9-2014 | Centering Payment for 3rd Slab | 25000 | Centering
157 | 14-9-2014 | Nageshwar For 3rd Floor Staircase | 2000 | Mason - Concrete
158 | 15-9-2014 | Tarpaulin for Store Room | 1750 | MISC
159 | 15-9-2014 | Steel for 3rd Slab only | 93400 | Steel
160 | 16-9-2014 | Electrical Material for 3rd Slab | 13600 | Electrical Material
161 | 18-9-2014 | Centering Payment | 20000 | CEntering
162 | 20-9-2014 | Steel for 3rd Slab | 12400 | Steel
163 | 20-9-2014 | Steel for fourth Floor Columns | 107400 | Steel
164 | 20-9-2014 | Centering Payment | 20000 | Centering
165 | 20-9-2014 | Concreting Payment | 20000 | Mason - Concrete
166 | 20-9-2014 | Bending Wire | 1900 | Steel
167 | 20-9-2014 | Kankar for 3rd Slab | 28000 | Kankar
168 | 20-9-2014 | Inaam for 3rd Slab | 2000 | MISC
169 | 22-9-2014 | Sand for Parking Area plastering | 21300 | Sand
170 | 20-9-2014 | Covering Boxes 2 | 600 | MISC
171 | 20-9-2014 | Petrol for 3rd Slab | 300 | MISC
172 | 20-9-2014 | Diesel 8 Ltrs | 514 | MISC
173 | 20-9-2014 | Lock for Store Room | 50 | MISC
174 | 22-9-2014 | Petrol for Pin | 100 | MISC
175 | 22-9-2014 | Oil 5 Ltrs | 150 | MISC
176 | 22-9-2014 | Tadkay | 1800 | Aminities - Gowa
177 | 22-9-2014 | Tadkay Transport | 300 | Aminities - Gowa
178 | 23-9-2014 | Lakdi Dumping Auto Charges | 300 | Aminities - Gowa
179 | 19-9-2014 | Auto for Electrical Material | 60 | MISC
180 | 19-9-2014 | Elec Material MISC | 200 | Electrical Material
181 | 20-9-2014 | Gobar | 20 | MISC
182 | 22-9-2014 | Iron Door for Elec Room | 2500 | Aminities - Fabrication
183 | 24-9-2014 | Mainhole Pipes & Covers | 13200 | Plumbing Material
184 | 24-9-2014 | Ganate 750 @ 11.60 | 8700 | MISC
185 | 24-9-2014 | Concretnig for 4th Flr Colounms | 10000 | Mason - Concrete
186 | 24-9-2014 | Elec Bill | 1816 | Utilities
187 | 26-9-2014 | RED Table Brick 5100 @ 3.40 | 17340 | Brick
188 | 26-9-2014 | Concrete for 4th Flr Columns | 10000 | Mason - Concrete
189 | 26-9-2014 | Cement for Plastering & Brick Work | 28000 | Cement
190 | 26-9-2014 | Gampay & Phoday MISC | 5000 | MISC
191 | 27-9-2014 | Centering Payment for 4th Flr Columns | 20000 | Centering
192 | 27-9-2014 | Ultra Tech Bircks 1800 @ 42 Each | 75600 | Brick
193 | 27-9-2014 | Plumber Payment for Drainage line | 4000 | Plumber
194 | 27-9-2014 | Ganet Payment | 3000 | Kankar
195 | 27-9-2014 | Brickwork Mason Payment | 28400 | Mason - Brick
196 | 29-9-2014 | Temp Bathroom Material | 5000 | MISC
197 | 29-9-2014 | Supervisor Salary | 9000 | UVI
198 | 30-9-2014 | Sand for 4th Slab | 61700 | Sand
199 | 30-9-2014 | Sand for Brick Work | 19300 | Sand
200 | 2014-01-10 | Carpente Material Hole Pass & Etc | 8100 | Wood
201 | 2014-01-10 | Steel for 4th Slab | 110030 | Steel
202 | 2014-02-10 | Gelden Heights Membership Society Fee | 10000 | Utilities
203 | 2014-01-09 | Oil for 4rth Slab | 200 | MISC
204 | 2014-02-10 | Watchman Salary | 5500 | Utilities
205 | 2014-02-10 | Plumber Payment for Drainage line | 16000 | Plumber
206 | 2014-02-10 | Taanchay for 3rd Flr | 1800 | MISC
207 | 2014-02-10 | Diesel for 4rth Slab | 150 | MISC
208 | 2014-02-10 | Goa Rassi | 140 | Aminities - Gowa
209 | 25-10-2014 | Mason Payment for Brick Work | 15900 | Mason - Brick
210 | 18-10-2014 | Mason Payment for Brick Work for 2 weeks | 50000 | Mason - Brick
211 | 25-10-2014 | Mason Work Under Dept | 4400 | Mason - Dept
212 | 29-10-2014 | Elec Bill | 2600 | Utilities
213 | 29-10-2014 | Oil for 5th Slab | 550 | MISC
214 | 25-10-2014 | Red Birck Light Weight | 28000 | Brick
215 | 25-10-2014 | Taanchay for 4th Slab | 1900 | Chipping
216 | 25-10-2014 | MISC by Supervisor | 500 | MISC
217 | 16-10-2014 | Steel for 4th Slab Balance | 90000 | Steel
218 | 2014-04-10 | Centering Payment for 4th Slab | 50000 | Centering
219 | 2014-04-10 | Nageshwar for Brick Work | 20600 | Mason - Brick
220 | 2014-04-10 | Electrition for 4th Slab | 4000 | Electrition
221 | 2014-04-10 | Carpenter for Frames Adv | 7000 | Wood
222 | 2014-11-10 | 200 Cement Bags @ 293 for 5th Slab | 58600 | Cement
223 | 22-10-2014 | Centering for 5th Flr Columns | 15000 | Centering
224 | 23-10-2014 | Transder of Sand from HH to RC (2k Bal)-Shoukath Bh | 3500 | Sand
225 | 24-10-2014 | Red Brick for Compund Wall | 13600 | Brick
226 | 24-10-2014 | Xtra Lite - 2nd Load | 75600 | Brick
227 | 25-10-2014 | Supervisor Salary | 8000 | UVI
228 | 2014-08-10 | Concreting for 4th Slab 18K + 7 K | 25000 | Mason - Concrete
229 | 2014-04-10 | Steel for 4th Slab | 80000 | Steel
230 | 30-10-2014 | Covering Blocks & oil for 5th Slab | 500 | MISC
231 | 29-10-2014 | Inaam for 4th Slab Centering | 1000 | MISC
232 | 24-10-2014 | Fixoblock Chemical From Ultratech | 31000 | Sand
233 | 2014-09-10 | Kankar for 4th Slab | 28000 | Kankar
234 | 22-10-2014 | Carpenter for Frames | 8000 | Wood
235 | 30-10-2014 | Steel for 5th Slab | 147305 | Steel
236 | 2014-02-10 | Mason Payment | 4000 | Mason - Brick
237 | 2014-03-10 | Electition Payment for 3rd Floor Slab | 4000 | Electrition
238 |  | Centering Payment for 4th Slab | 10000 | CEntering
239 | 2014-08-10 | Cement 100 Bags @ 293 for 4th Slab | 29300 | CEment
240 | 2014-08-10 | Cement 100 Bags @ 283 for Brick Work | 22640 | Cement
241 | 2014-01-11 | Mason Payment for Brick Work | 12800 | Mason - Brick
242 | 2014-02-11 | Centering Payment for 5th Slab | 35000 | Centering
243 | 2014-02-11 | Electrical Material for 5th Slab | 7800 | Electrical Material
244 | 2014-02-11 | Watchman Salary 6K+ 5 Inaam + 2K Adv | 8500 | Utilities
245 | 2014-02-11 | Carpenter for frames | 5000 | Wood
246 | 2014-03-11 | Cement for 5th Slab 100 Bags@ 273 -53 Chettinad | 27300 | Cement
247 | 2014-03-11 | Cement for Plastering 50 Bags @ 265-43 Chettinad | 13400 | Cement
248 | 2014-03-11 | Steel for 5th Floor + old Bal (80700) | 100000 | Steel
249 | 2014-03-11 | Brick Cutting Machine + Blades | 2080 | MISC
250 | 2014-03-11 | Sand for 5th Floor 25 Tons @ 11.40 Per ton + Weight | 28700 | Sand
251 | 2014-04-11 | Sand for 5th Floor 17 Tons @ 10.20 Per ton + Weight | 17080 | Sand
252 | 2014-04-11 | Petrol & Newspaper for 5th Floor | 250 | MISC
253 | 2014-04-11 | Inaams for 5th Slab-Watchman+Labour+Mestry | 1500 | MISC
254 | 2014-04-11 | Electrition payment for 5th Slab | 4000 | Electrition
255 | 2014-05-11 | Red Brick for Lift Are & compund Wall 3500 @ 5 | 18000 | Brick
256 | 2014-05-11 | Kankar Payment for 5th Slab(8K Bal) | 28000 | Kankar
257 | 2014-04-11 | Cencreting Payment for 5th Slab (25 Bal) | 10000 | Mason - Concrete
258 | 2014-05-11 | Extra African wood for Cuddappa | 1500 | Wood
259 | 2014-05-11 | Centering Payment for 5th Slab(20 K Bal) | 20000 | Centering
260 | 2014-07-11 | Plumber Payment for 2 Bathrooms Line | 20000 | Plumber
261 | 2014-12-11 | Transfer of MISC items from RH to RC | 900 | MISC
262 | 2014-12-11 | Ultra Tech Bircks 3600 @ 42 Each | 151200 | Brick
263 | 15-11-2014 | Centering Payment for Last Slab (10 K Bal) | 11000 | Centering
264 | 17-11-2014 | Rethi for Lift Slab & Plastering | 22700 | Sand
265 | 18-11-2014 | Excavation for Drain Line | 700 | Excavation
266 | 25-11-2014 | Sand for Outer Plastering | 20600 | Sand
267 | 20-11-2014 | Centering Payment for Chajjay | 5000 | Centering
268 | 27-11-2014 | Centering Payment for Lift Slabs- Adv | 10000 | Centering
269 | 27-11-2014 | Mason for two Months - 1 Month Adv & 1 Month Balance | 200000 | Mason - Brick
270 | 26-11-2014 | Tannchay for fifth Slab | 1800 | Chipping
271 | 26-11-2014 | Power Scokets | 350 | Electrical Material
272 | 2014-02-12 | Centering (9K) + 11K for Chajjay | 20000 | Centering
273 | 2014-02-12 | Oil & Bending Wire | 500 | MISC
274 | 2014-02-12 | Brick Cutting Machine Repiair | 500 | MISC
275 | 2014-03-12 | Mirza Steels | 80700 | Steel
276 | 2014-03-12 | Brick Light Weight (Red) | 27500 | Brick
277 | 2014-08-12 | Centering Payment for 1st & 2nd Flr Chajjay & Lift Work Adv | 17400 | Centering
278 | 2014-06-12 | Plumber Payment - Not Matched with Qasim record | 5000 | Plumber
279 | 2014-06-12 | Printer | 3700 | UVI
280 | 2014-09-12 | Cement 300 Bags @ 293 for Plastering Penna 43 | 88000 | Cement
281 | 2014-09-12 | Tipper Balance for Material Transfer | 2000 | MISC
282 | 2014-09-12 | Curing Pipe & Others | 700 | MISC
283 | 2014-12-12 | Gowa Lakdi & Tadkay | 10000 | Aminities - Gowa
284 | 13-12-2014 | Gowa Tieing Charges @ 1.5 Per SFT - Adv 5K + Payment 10K Bal 4K | 15700 | Aminities - Gowa
285 | 13-12-2014 | Sand for Outer Plastering @ 12.30 per ton (Double Filter) | 27900 | Sand
286 | 13-12-2014 | First Floor Bathroom Water Proofing (Office) | 1400 | Water Proofing
287 | 13-12-2014 | Safety Belts | 750 | MISC
288 | 13-12-2014 | Old Gowa Lakdi | 18000 | Aminities - Gowa
289 | 13-12-2014 | Gowa Rassi (24 Bundles) | 4800 | Aminities - Gowa
290 | 13-12-2014 | Old Lakdi | 1600 | Aminities - Gowa
291 | 13-12-2014 | Gowa Lakdi Looding & Unloading | 500 | Aminities - Gowa
292 | 13-12-2014 | Curing Pipe | 600 | MISC
293 | 13-12-2014 | Tadkay | 1800 | Aminities - Gowa
294 | 13-12-2014 | Plumber Payment | 6500 | Plumbing Material
295 | 14-12-2014 | Gowa Lakdi & Taday | 12400 | Aminities - Gowa
296 | 14-12-2014 | Old Gowa Lakdi | 1500 | Aminities - Gowa
297 | 18-12-2014 | AAC Blocks from ACC Company @ 40 X 800 | 33600 | Brick
298 | 19-12-2014 | Electrical Material ( Pipes, Iron Boxes, & MCB Boxes Etc.,) | 36350 | Electrical Material
299 | 20-12-2014 | Gowa Balance | 4000 | Aminities - Gowa
300 | 20-12-2014 | Centering Payment for 3rd Flr Chajjay & Lift Work Bal Partly | 12000 | Centering
301 | 20-12-2014 | Payment for Mason (Lifting Material) | 20000 | Mason - Brick
302 | 22-12-2014 | Two Months Elec Bill | 4844 | Utilities
303 | 23-12-2014 | 200 Bricks @5.50 + Transport | 1000 | Brick
304 | 23-12-2014 | Brick from Perli | 26150 | Brick
305 | 23-12-2014 | Sand for Plastering 12.20 Per ton | 61100 | Sand
306 | 24-12-2014 | Gate Fabrication | 25000 | Aminities - Fabrication
307 | 24-12-2014 | CPVC Internal Fittings Material | 15750 | Plumbing Material
308 | 27-12-2014 | Plumber Payment for Chipping | 5000 | Chipping
309 | 26-12-2014 | CPVC Internal Fittings Material | 19235 | Plumbing Material
310 | 30-12-2014 | 200 SFT Kankar | 5000 | Kankar
311 | 30-12-2014 | Payment for Mason (Lifting Material) | 10000 | Mason - Brick
312 | 31-12-2014 | Plumber Payment for Chipping | 8000 | Chipping
313 | 31-2-2014 | Plumber Payment for CPVC Fittings | 20000 | Plumber
314 | 31-12-2014 | CPVC Internal & Outer Fittinf Material | 37000 | Plumbing Material
315 | 2015-01-01 | Blocks Bricks 41 X 600 | 24600 | Brick
316 | 2015-01-01 | Legrand Boxes | 6300 | Electrical Material
317 | 2015-02-01 | Electrical Material | 36500 | Electrical Material
318 | 2015-03-01 | Electrition Payment for Chipping, Piping & Box Fixing | 20000 | Electrition
319 | 2015-03-01 | Mason Payment | 59000 | Mason - Brick
320 | 2015-03-01 | Cutting Blade & MISC | 560 | MISC
321 | 2015-06-01 | Watchman Salary | 5000 | Utilities
322 | 2015-07-01 | Kabutar Jali & MISC | 500 | MISC
323 | 2015-08-01 | Safety Grills for Office | 5300 | Fabrication - Flats
324 | 2015-08-01 | Doors for Office (Bedroom, bathroom & Balcony) | 11000 | Wood
325 | 2015-12-01 | Cement Bags 4 | 1180 | Cement
326 | 2015-12-01 | Centering Final Payment for Chajja, Lift & Gate Work | 16000 | Centering
327 | 2015-12-01 | Mason Adv @ Snkratri | 100000 | Mason - Brick
328 | 2015-12-01 | Plumbing MISC | 3390 | Plumbing Material
329 | 15-1-2015 | Plumber Payment for CPVC Fittings | 10000 | Plumber
330 | 16-1-2015 | Cement Bags 100 @ 310 Penna 43 | 31000 | cement
331 | 15-1-2015 | Brick from Naseer Bh | 19000 | Brick
332 | 20-1-2015 | Supervisor Salary | 12000 | UVI
333 | 24-01-2015 | Brick | 6000 | Brick
334 | 27-1-2015 | Office Glass & fittings | 1700 | Fabrication - Flats
335 | 27-1-2015 | Table Glass | 2400 | UVI
336 | 27-1-2015 | Mason - Brick Work Payment | 41000 | Mason - Brick
337 | 31-1-2015 | Electrition Payment for Chipping, Piping & Box Fixing | 10000 | Electrition
338 | 30-1-2015 | Bidding & Other MISC | 500 | MISC
339 | 2015-02-02 | Mason Payment | 12200 | Mason - Brick
340 | 2015-02-02 | Watchman Salary | 5000 | Utilities
341 | 2015-02-02 | Jagdambda MISC | 10000 | MISC
342 | 2015-04-02 | Sand | 4000 | Sand
343 | 2015-04-02 | Plumber Payment PVC Fitting Adv | 5000 | Plumber
344 | 2015-02-02 | Office Shifting & PC Maintenance | 2500 | UVI
345 | 2015-09-02 | Water Proofing Payment | 5000 | Water Proofing
346 | 2015-09-02 | JCB for Site Cleaning | 1500 | MISC
347 | 2015-11-02 | Mason Payment for Bricks | 15000 | Mason - Brick
348 | 18-2-2015 | Cement Bags 200 @ 309 Penna 43 | 61800 | Cement
349 | 19-2-2015 | Elec Bill | 5600 | Utilities
350 | 14-2-2015 | Mason Payment | 15000 | Mason - Brick
351 | 21-2-2015 | Inverter fo Office | 21000 | UVI
352 | 25-2-2015 | Plumber Extra Labour charges for PVC & CPVC for Front Balcony | 2000 | Plumber
353 | 27-02-2015 | Plumber Payment for PVC | 10000 | Plumber
354 | 26-2-2015 | Water Proofing 2nd Payment | 5000 | Water Proofing
355 | 28-2-2014 | Mason - Brick - two weeks | 25000 | Mason - Brick
356 | 2015-01-03 | Sand for Plastering | 34500 | Sand
357 | 26-2-2015 | MISC Plumbing From Jagdamba | 10000 | Plumbing Material
358 | 2015-01-03 | PVC Material From AP | 40436 | Plumbing Material
359 | 28-2-2015 | Kabutar Jali for Water Proofing | 225 | MISC
360 | 2015-04-03 | Plumbing PVC MISC | 970 | Plumbing Material
361 | 2015-10-01 | MISC for UVI | 610 | UVI
362 | 2015-03-03 | Payment for lifing sand | 5000 | Mason - Brick
363 | 2015-04-03 | Steel for All Chajjas, Lift's Slabs & 16 MM for Few Coloumns | 80000 | steel
364 | 2015-07-03 | Mason - Brick Payment | 25800 | Mason - Brick
365 | 2015-07-03 | Plumber Payment for PVC Fittings | 15000 | Plumber
366 | 2015-07-03 | Water Proofing Payment | 15000 | Water Proofing
367 | 2015-09-03 | Watchman Salary | 5500 | Utilities
368 | 2015-10-03 | Meter Shifting from Elec Dept | 500 | Utilities
369 | 2015-11-03 | Plumber Payment for Complete of 8 Flats PVC & CPVC Fittings Balance Amount 17K it will be paid at the time of final Fitting | 3000 | Plumber
| 2015-03-11 | Temp Office Fittings | 1000 | MISC
370 | 2015-11-03 | Sand for first coat plastering 23 Tons @ 15.20 | 35100 | Sand
371 | 2015-11-03 | Mason payment for sand Lfting | 3500 | Mason - Brick
373 | 18-3-2015 | Cement BAGS 200 @ 310 | 62000 | CEment
374 | 17-3-2015 | Cement Bags 10 @ 330 | 3380 | Cement
375 | 21-3-2015 | Stone Excavation | 1000 | Excavation
376 | 21-3-2015 | Steel & Oil for Parbola | 1400 | MISC
377 | 20-3-2015 | Watchman Adv | 1000 | Utilities
378 | 21-3-2015 | Mason Payment for two Weeks | 40000 | Mason - Brick
379 | 23-3-2015 | Plumbing MISC | 2431 | Plumbing Material
380 | 31-3-2015 | Mason Payment | 16500 | Mason - Brick
381 | 31-3-2015 | Sand Kurnool 40.6 Tons @ 1800 + Weight | 73300 | Sand
382 | 2015-01-03 | Chipping for extra beams & all | 5000 | Chipping
383 | 2015-02-03 | Adv for Glass Frame | 10000 | Aminities - Fabrication
384 | 2015-02-03 | Advance for Railing @ balcony Site | 20000 | Fabrication - Flats
385 | 2015-04-04 | Mason Payment | 23700 | Mason - Brick
386 | 2015-08-04 | Fabrication for round Railing | 2000 | Fabrication - Flats
387 | 2015-11-04 | Fabrication for glass frame (Ateeq) | 18800 | Aminities - Fabrication
388 | 2015-11-04 | Round Railing Sample Railing | 2300 | Fabrication - Flats
389 | 2015-11-04 | Mason Payment | 30700 | Mason - Brick
390 | 2015-11-04 | Watchman salary | 4500 | Utilities
391 | 2015-05-04 | Fabrication for round railing (Sauleh) | 20000 | Fabrication - Flats
392 | 2015-10-04 | Centering Payment for Parbola (Boxes Damaged) | 5000 | Centering
393 | 13-4-2015 | MISC for Rassi | 500 | MISC
394 | 14-4-2015 | Payment for round Railing | 14000 | Fabrication - Flats
395 | 16-4-2015 | Painter Payment - First Time | 5000 | Painter
396 | 16-4-2015 | Mason Payment | 23800 | Mason - Brick
397 | 17-4-2015 | Loose Bricks | 5300 | Brick
398 | 24-4-2015 | Final Payment Sauleh | 5200 | Fabrication - Flats
399 | 23-4-2015 | Water Proofing Payment | 1500 | Water Proofing
400 | 26-4-2015 | Mason Payment | 16000 | Mason - Brick
401 | 26-4-2015 | Painter Payment | 20000 | Painter
402 | 27-4-2015 | Paint MISC Material | 1100 | Painter Material
403 | 27-4-2015 | Elec Bill | 6900 | Utilities
404 | 29-4-2015 | MISC Exp | 170 | MISC
405 | 2015-02-05 | Mason Payment | 19000 | Mason - Brick
406 | 2015-02-05 | Painter Payment | 12000 | Painter
407 | 2015-02-05 | Elec MISC Material | 1950 | Electrical Material
408 | 2015-02-05 | Adv for Elev Stones | 30000 | Aminities - Elevation
409 | 2015-05-05 | UVI Rexine & Others MISC | 520 | UVI
410 | 2015-05-05 | AAC Blocks for 4th Floor | 9200 | Brick
411 | 2015-09-05 | Mason Payment | 20000 | Mason - Brick
412 | 2015-09-05 | Painter Payment | 10000 | Painter
413 | 2015-09-05 | Watchman Salary | 5500 | Utilities
414 | 2015-11-05 | Elevation Glasses 60 @ 46 /SFT | 11500 | Aminities - Elevation
415 | 2015-12-05 | Cement Bags 70 @ 308 | 21560 | Cement
416 | 2015-12-05 | 6 & 8 MM Steel for Archs | 5000 | Steel
417 | 2015-12-05 | Locks for Main gate, Store Room & MISC | 1400 | MISC
418 | 14-5-2015 | Elevation Glasses fixer | 3400 | Aminities - Elevation
419 | 16-5-2015 | Mason Payment | 15000 | Mason - Brick
420 | 16-5-2015 | Painter payment | 12000 | Painter
421 | 16-5-2015 | Arch Wood Frames | 500 | MISC
422 | 17-5-2015 | Double gowa for Stones | 3000 | Aminities - Gowa
423 | 23-5-2015 | Elevation Stones Fixer Payment | 7000 | Aminities - Elevation
424 | 23-5-2015 | Elevation Stones 2nd Payment | 40000 | Aminities - Elevation
425 | 2015-05-22 | Kurnool Sand for Plastering | 48000 | Sand
425 | 23-5-2015 | Lappum for four Flats | 8500 | Painter Material
426 | 23-5-2015 | Birla Putty for Exterior | 10000 | Painter Material
427 | 23-5-2015 | Exterior Premier & Others | 5560 | Painter Material
428 | 23-5-2015 | Birla Putty for Exterior | 20400 | Painter Material
429 | 23-5-2015 | Paint MISC Material (Patty & Papers) | 720 | Painter Material
430 | 23-5-2015 | Mason Payment | 5000 | Mason - Brick
431 | 25-5-2015 | Elevation Stones Fixer Payment | 8000 | Aminities - Elevation
432 | 25-5-2015 | Electrition Payment for Chipping, Piping & Box Fixing | 7000 | Electrition
433 | 25-5-2015 | Chipping for Kitchens Arches | 2200 | Chipping
434 | 2015-05-30 | Mason Payment | 45000 | Mason - Brick
435 | 2015-05-03 | Brick for Lift work & balcony | 12330 | Brick
436 | 2015-05-30 | Painter Payment | 15000 | Painter
437 | 2015-05-30 | Magma Fin Personal (37000) | 0 | Personal
438 | 2015-05-30 | Cement bags | 16175 | Cement
439 | 2015-06-02 | Elec Bill | 3560 | Utilities
440 | 2015-06-05 | Setback cleaning for OC inspection | 1900 | MISC
441 | 2015-06-05 | Chipping | 2700 | Chipping
443 | 2015-06-06 | Elevation Stone Fixers | 15000 | Aminities - Elevation
444 | 2015-06-11 | Parking Cleaning for Inspection | 1200 | MISC
445 | 2015-06-11 | Watchman Salary | 6500 | Utilities
446 | 2015-06-10 | False Ceiling Adv for Flats | 10000 | False Ceiling
| 2015-06-08 | Electric Wire Sample | 2350 | Electrical Material
447 | 2015-06-11 | Electrical Wires for 4 Flats, Parking & Main lines | 97000 | Electrical Material
448 | 2015-06-12 | Flats Main doors | 40000 | Wood
449 | 2015-06-12 | Painter Payment | 15000 | Painter
450 | 2015-06-14 | Mason Payment | 15000 | Mason - Brick
451 | 2015-06-18 | Safety Grills Adv - Azghar | 10000 | Fabrication - Flats
452 | 2015-06-18 | Payment to Jagdamba for MISC Elec & others | 15000 | Electrical Material
453 | 2015-06-18 | UPVC Windows for 1 & 2 Fls Adv | 80000 | UPVC
454 | 2015-06-19 | Flats Main Doors HW | 11820 | Wood
455 | 2015-06-20 | Painter Payment | 18000 | Painter
456 | 2015-06-20 | Electrition Payment | 4000 | Electrition
457 | 2015-06-20 | Mason Payment | 10000 | Mason - Brick
458 | 2015-06-22 | Cement Bags | 15380 | Cement
459 | 2015-06-20 | MISC Work Labour | 400 | Misc
460 | 2015-06-21 | Main doors fittings flats 1 & 2 Fls | 1000 | Wood
461 | 2015-06-22 | Paint Material MISC | 700 | Misc
462 | 2015-06-22 | Watchman Salary Adv | 2000 | Utilities
463 | 2015-06-24 | False Ceiling 2nd Payment | 10000 | False Ceiling
464 | 2015-06-24 | GHMC DD Payment for OC | 160000 | Aminities - GHMC
465 | 24-60-2015 | GHMC Payment for OC - BRB | 60000 | Aminities - GHMC
466 | 2015-06-24 | Polish for flats 1 & 2 FLR | 4000 | Polish
467 | 2015-06-24 | Sump Motor Servicing | 1250 | Misc
468 | 2015-06-27 | Elec Payment | 5000 | Electrition
469 | 2015-06-27 | Mason Payment | 15000 | Mason - Brick
470 | 2015-06-27 | Painter Payment | 14000 | Painter
471 | 2015-06-28 | Safety Grills Payment - Azghar | 15000 | Fabrication
472 | 29-6--2015 | Polish for flats 1 & 2 FLR - 2nd Payment | 6000 | Polish
473 | 2015-07-02 | Elec Bill | 4000 | Utilities
474 | 2015-07-02 | Gowa Tieing for Lift Plastering | 1500 | Aminities - Gowa
475 | 2015-07-02 | Water Proofing for Balconies - ADV | 5000 | Water Proofing
476 | 2015-07-02 | Painter Payment | 9000 | Painter
477 | 2015-07-05 | Sand for Plastering Lift 7 Compund Wall | 26000 | Sand
478 | 2015-07-10 | Safety Grills Payment - Azghar | 7500 | Fabrication
479 | 2015-07-11 | Mason Payment | 15000 | Mason - Brick
480 | 2015-07-11 | Watchamn Salary | 5000 | Utilities
481 | 2015-07-11 | Painter Payment | 5000 | Painter
482 | 2015-07-11 | Granite for Kitchen Platforms | 40000 | Granite
483 | 2015-07-11 | Safety Grills ADV for 3 & 4 Flr - Azghar | 20000 | Fabrication
484 | 2015-07-16 | Cement 70 Bags | 20000 | Cement
485 | 2015-07-16 | Supervisor Salary | 11000 | UVI
486 | 2015-07-16 | Lift ADV - Metro Elevators | 114500 | Aminities - Lift
487 | 2015-07-16 | Electrical Final Fittings & mcbS | 50000 | Electrical Material
488 | 2015-07-16 | Brick | 21000 | Brick
489 | 2015-07-16 | Water Proofing for Baclony | 5000 | Water Proofing
490 | 2015-07-16 | Electrition Payment | 10000 | Electrition
491 | 2015-07-21 | Mason Payment | 15000 | Mason - Brick
492 | 2015-07-23 | Watchman Salary ADV | 5000 | Utilities
493 | 2015-07-23 | Sand for Compund Wall | 15000 | Sand
494 | 2015-07-23 | Supervisor ADV - Mobile | 4000 | UVI
495 | 2015-07-24 | Payment to Jagdamba including one cera Basin | 13000 | Misc
496 | 2015-07-24 | Gowa Tieing for Lift Work | 2500 | Aminities - Gowa
497 | 2015-07-24 | Painter Advance | 20000 | Painter
498 | 2015-07-24 | Mason Payment | 15000 | Mason - Brick
499 | 2015-07-25 | 12 Bathrooms & 4 Kitchens Wall Tiles | 70500 | Tiles
500 | 2015-07-25 | 12 Bathrooms & 4 Kitchens Wall Tiles - Trans & Lab | 2800 | Tiles
501 | 2015-07-25 | Chipping for Lift Work | 2200 | Chipping
502 | 2015-07-27 | Painter Payment | 5000 | Painter
503 | 2015-07-27 | Lifting Sand for Tiles Work | 2200 | Misc
504 | 2015-09-29 | Granite Fixinf gor Kitchens | 3000 | Granite Fixer
505 | 2015-07-30 | Birla Putty for Exterior | 10200 | Painter Material
506 | 2015-07-30 | Additional Tiles | 2500 | Tiles
507 | 2015-08-02 | Fabrization Grills Payment for 3 & 4 Flr 28 Grills (10K Bal) | 25000 | Fabrication
508 | 2015-08-02 | Labour for Lifting Granite - Ismail Bh | 1000 | Misc
509 | 2015-08-02 | Sand for Tiles & Mason Work | 22000 | Sand
510 | 2015-08-01 | Tiles Fixer Payment - Munaaf Bh | 18000 | Tiles Fixer
511 | 2015-08-01 | Electrition Payment | 10000 | Electrition
512 | 2015-08-01 | Painter Payment | 10000 | Mason - Brick
513 | 2015-08-01 | Mason Payment | 10000 | Painter
514 | 2015-08-01 | MISC Labour Watchman Wife | 2000 | Misc
515 | 2015-08-01 | MISC Expenses by Supervisor | 800 | Misc
516 | 2015-08-03 | Cement bags (23K Bal) | 40000 | Cement
517 | 2015-08-03 | Internet & Phone Bill (UVI) | 6000 | UVI
518 | 2015-08-03 | Paid for OC BRB & Service Charges | 60000 | Aminities - GHMC
519 | 2015-08-03 | Documentation for Mortgage Release | 5500 | Aminities - GHMC
520 | 2015-08-03 | Centering Payment for Kitchen Platforms | 6000 | Centering
521 | 2015-08-04 | Marble for staircase | 64500 | Aminities - Marble
522 | 2015-08-06 | Granite for staircase - Center 6" Patta | 6100 | Granite
523 | 2015-08-04 | Tiles Fixer Seconf Payment | 7000 | Tiles Fixer
524 | 2015-08-06 | MISC Exp by Spervisor | 400 | Misc
525 | 2015-08-07 | A.P Traders - Paint Material | 47000 | Painter Material
526 | 2015-08-07 | AP Traders Sink for Flats (Nirali) (4Pc) | 19800 | Misc
527 | 2015-08-08 | Mason Payment | 10000 | Mason - Brick
528 | 2015-08-08 | Painter Payment | 10000 | Painter
529 | 2015-08-07 | AP Traders Electrical Materials | 20000 | Electrical Material
530 | 2015-08-07 | Electrition Payment | 10000 | Electrition
531 | 2015-08-06 | MISC Exp for PC | 1200 | UVI
532 | 2015-08-06 | Marble Flooring ADV forBhayya's & my flat @ 3 & 4 Flr | 55000 | Marble
533 | 2015-08-06 | Teak Doors Adv for 3 & 4 Flr | 20000 | Wood
534 | 2015-08-06 | Teak frame for 5th FLR one frame only | 3000 | Wood
535 | 2015-08-08 | Granite fixing Payment for Kitchens | 5000 | Granite Fixer
536 | 2015-08-10 | Watchman Salary | 2000 | Utilities
537 | 2015-08-10 | MISC Labour Watchman Wife | 2200 | Misc
538 | 2015-08-10 | Tiles Fixer - Minaaf Bhai | 8000 | Tiles Fixer
539 | 2015-08-11 | Water Proofing for Baclony | 3000 | Water Proofing
540 | 2015-08-10 | Granite fixing Payment for Kitchens | 7000 | Granite Fixer
541 | 2015-08-08 | False Ceiling Final Payment for 1 & 2nd Flr | 23500 | False Ceiling
542 | 2015-08-08 | False Ceiling Adv Payment for 3 & 4 Flr | 15000 | False Ceiling
543 | 2015-08-15 | Flats Number Plates | 500 | Misc
544 | 2015-08-08 | Mason Payment | 10000 | Mason - Brick
545 | 2015-08-17 | Sand for Flooring & Plastering | 17000 | Sand
546 | 2015-08-17 | Brick for Watchman room & Landscaping | 10500 | Brick
547 | 2015-08-20 | Granite fixing Payment for Kitchens | 7000 | Granite Fixer
548 | 2015-08-22 | Painter Payment | 2000 | Painter
549 | 2015-08-24 | Granite fixing Payment for Kitchens | 5000 | Granite Fixer
550 | 2015-08-24 | Bed Material | 10000 | Kankar
551 | 2015-08-28 | Bed Labour | 3500 | Misc
552 | 2015-09-01 | Elec Bill | 4239 | Utilities
553 | 2015-09-01 | Staircase & Kitchen Granite Final Payment | 5000 | Granite Fixer
| 2015-09-01 | Parking Flooring Adv | 5000 | Aminities - Parking Flooring
554 | 2015-09-01 | Mason Payment | 10000 | Mason - Brick
555 | 2015-09-01 | Steel Old Balance | 9000 | Steel
556 | 2015-09-01 | Main Doors for 3Rd & 4th Final Payment | 24000 | Wood
557 | 2015-09-03 | Sand Lifting for Flooring | 5000 | Sand
558 | 2015-09-03 | Parking Flooring Stone + Labour | 40500 | Aminities - Parking Flooring
559 | 2015-09-03 | Cement Balance | 15000 | Cement
560 | 2015-09-03 | Kankar & Ganate | 4500 | Kankar
561 | 2015-09-03 | Mason Payment | 15000 | Mason - Brick
562 | 2015-09-05 | Electrition Payment | 10000 | Electrition
563 | 2015-09-05 | Supervisor Salary | 10000 | UVI
564 | 2015-09-05 | Watchman Salary | 5000 | Utilities
565 | 2015-09-05 | Tiles ADV for Flat 101 & 102 | 20000 | Tiles
566 | 2015-09-06 | Brick for Landscaping | 5000 | Brick
567 | 2015-09-06 | Frames for Watchmand Room & Transport | 4000 | Wood
568 | 2015-09-06 | Plastering Sand from Rizwan Bh | 2000 | Sand
569 | 2015-09-06 | Jagdamba Payment | 10000 | Misc
570 | 2015-09-07 | Plumber Payment for Parking Bathroom (3k Bal) | 5000 | Plumber
571 | 2015-09-08 | Gowa Lakdi & MISC Material from Hassan Saab | 4000 | Aminities - Gowa
572 | 2015-09-08 | Ganate for Landscaping | 6000 | Kankar
573 | 2015-09-09 | Grills for Inside Landscaping | 30000 | Aminities - Fabrication
574 | 2015-09-09 | Tiles final Payment | 63000 | Tiles
575 | 2015-09-09 | Granite for lift area & Others | 26000 | Granite
576 | 2015-09-09 | Paint Material for Ceiling | 6000 | Painter Material
577 | 2015-09-19 | Tiles Fixer Munaaf Bh for Flat 101 & 102 | 17000 | Tiles Fixer
578 | 2015-09-12 | Tiles for Balcony floor & Wall | 10000 | Tiles
579 | 2015-09-14 | MISC Labour for Lanscaping | 5150 | Misc
580 | 2015-09-15 | MISC Labour | 1350 | Misc
581 | 2015-09-14 | Bidding for two Floors | 3500 | Wood
582 | 2015-09-19 | Dust for Flooring | 21000 | Sand
583 | 2015-09-19 | MISC Tiles for 101 & 102 Flats | 1700 | Tiles
584 | 2015-09-19 | Mason Payment | 8000 | Mason - Brick
585 | 2015-09-19 | Polish Main Doors Payment for 3 & 4th Flr | 5000 | Polish
586 | 2015-09-19 | Parking Flooring Payment Ismail Bh | 7000 | Aminities - Parking Flooring
587 | 2015-09-19 | Lift Granite Fixer - AlaUddin | 9000 | Granite Fixer
588 | 2015-09-22 | Tiles for Supervier Home | 4100 | UVI
589 | 2015-09-22 | Tiles fixer Payment for Supervisor Home | 2000 | UVI
590 | 2015-09-22 | MISC Exp by Spervisor | 1500 | Misc
591 | 2015-09-23 | Hardware for Main Doors 3 & 4 Flr | 12260 | Wood
592 | 2015-09-16 | Water Connection 1 Payment | 22000 | Aminities - Water Dept
593 | 2015-09-15 | Transfarmet 1st Payment | 50000 | Aminities - Electrical Dept
594 | 2015-09-15 | Windows Final Payment for 101 & 102 | 70000 | UPVC
595 | 2015-09-19 | Windows Adv Payment for 3 & 4 Flr | 40000 | UPVC
596 | 2015-09-19 | Mota Kanakar for Bed | 4500 | Kankar
597 | 2015-09-19 | Painter Payment | 7000 | Painter
598 | 2015-09-10 | Paint for 1 & 2 Flr | 15000 | Painter Material
599 | 2015-09-24 | Paid for Polish to JAHANGIR | 5000 | Polish
600 | 2015-09-24 | Paid to AlaUddin for Lift Granite Work | 8000 | Granite Fixer
601 | 2015-09-24 | Paid to Ismail Bh for Parking | 6000 | Aminities - Parking Flooring
602 | 2015-09-17 | Paid to Carpenter for Watchman Room & Bathroom Frames & Door | 1000 | Wood
603 | 2015-10-06 | Paid to Ismail Bh for Parking | 5000 | Aminities - Parking Flooring
604 | 6/20/2015 | Painter Payment | 20000 | Painter
605 | 2015-10-06 | Bidding for all doors including Main Doors | 9000 | Wood
606 | 2015-10-06 | Granite for Parking Tiles & Slab | 12000 | Aminities - Parking Flooring
607 | 2015-10-12 | Transfarmer - PDC 2nd Payment | 30000 | Aminities - Electrical Dept
608 | 2015-10-05 | Carpenter for Bidding | 2000 | Wood
609 | 2015-10-08 | Carpenter for Bidding | 2500 | Wood
610 | 2015-10-08 | Granite Tiles for Parking | 5100 | Aminities - Parking Flooring
611 | 2015-09-01 | Supervisor Salary | 8000 | UVI
612 | 2015-10-08 | Watchman Bathroom Material | 1880 | Wood
613 | 2015-10-15 | AP Traders | 15000 | Misc
614 | 2015-10-15 | Cement Balance | 23000 | Cement
615 | 15-/10/2015 | MISC | 2210 | Misc
616 | 2015-10-15 | Watchman Salary | 6000 | Utilities
617 | 2015-10-15 | Transfarmer Second Payment |  | Aminities - Electrical Dept
618 | 2015-10-16 | Tiles Fixer Payment | 5000 | Tiles Fixer
619 | 2015-10-16 | Parking Payment Ismail Bh | 7000 | Aminities - Parking Flooring
620 | 2015-10-16 | Plumbing MISC Material | 1000 | Plumbing Material
621 | 2015-10-08 | Windows Cutting MISC I | 1000 | Misc
622 | 2015-10-16 | MISC Exp By Sup | 680 | Misc
623 | 2015-10-16 | MISC Lab for Earth Pits | 400 | Misc
624 | 2015-10-16 | Elevation Stone Fixers | 3200 | Aminities - Elevation
625 | 2015-10-15 | Carpenter For Doors Bidding | 2500 | Wood
626 | 2015-10-17 | Nageshwar for Brick Work | 10000 | Mason - Brick
627 | 2015-10-18 | Jagdamba Payment | 10000 | Misc
628 | 2015-10-16 | Qasim Plumber - Not Match with Qasim Record | 2000 | Plumber
629 | 2015-10-19 | Elec Bill | 4200 | Utilities
630 | 2015-10-22 | Dust for Parking | 14000 | Sand
631 | 2015-10-22 | Parking Work Payment Ismail Bh | 4000 | Aminities - Parking Flooring
632 | 2015-10-22 | MISC Labour | 500 | Misc
633 | 2015-10-22 | Centering Adv for Slab 5 & 6th | 10000 | Centering
634 | 2015-10-22 | MISC Exp | 600 | Misc
635 | 2015-10-25 | Tiles Adv for Flat 201,301 & 302) 32X32 & 2X2 | 76000 | Tiles
636 | 2015-10-26 | Wiring Polycab payment for Flat 301 & 302 | 15000 | Electrical Material
637 | 2014-10-27 | Tiles for Balconies & Kitchen @ 3rd Floor | 18000 | Tiles
638 | 2015-10-27 | Azeem Personnel - 30000 | 0 | Personal
639 | 2015-10-26 | Dust Lifting for Flooring | 2800 | Misc
640 | 2015-10-28 | Flat # 1 & 2 @ 1st Flr Doors Hardware | 23000 | Wood
641 | 2015-10-27 | Earthing Material | 21000 | Electrical Material
642 | 2015-10-28 | False Ceiling Payment | 8000 | False Ceiling
643 | 2015-10-29 | 12 Doors Payment for Flat # 1 & 2 @ 1st Flr @ 95/SFT | 20000 | Wood
644 | 2015-10-29 | Earth Pits Bore 3200 X 6 | 15500 | Electrical Material
645 | 2015-10-30 | Electrical Wires for 3 & 4 Flats | 28000 | Electrical Material
646 | 2015-10-30 | Tiles for 3 & 4 Flr Balconies & Kitchen | 8300 | Tiles
647 | 2015-10-30 | 2nd Final Payment for 2 & 3 Flr 2X2 Tiles for Bedrooms | 30000 | Tiles
648 | 2015-10-31 | Sanitory Adv Bal (30K) | 53400 | Sanitory
649 | 2015-10-31 | Cement for 75 Bags | 20340 | Cement
650 | 2015-10-31 | Tiles Fixer Payment Munaaf Bh | 10000 | Tiles Fixer
651 | 2015-10-31 | Electrition Payment (Sultan Bh) | 5000 | Electrition
652 | 2015-10-31 | Chary Carpenter for Bedroom & Bathroom Doors | 3000 | Wood
653 | 2015-10-30 | PVC Sheet & SR | 1300 | Wood
654 | 2015-11-02 | Watchman salary | 6000 | Utilities
655 | 2015-11-02 | Supervisor Salary | 8000 | Utilities
656 |  | Dust for Flooring | 7000 | Sand
657 |  | Upvc Payment | 80000 | UPVC
658 |  | Doors Polish Adv | 8000 | Wood
659 |  | Tiles for 3rd Flr Bathroom | 22500 | tiles
660 | 2015-11-06 | False Ceiling Payment | 10000 | False Ceiling
661 |  | Carpenter Payment for Doors | 3000 | Wood
662 |  | Tiles final payment for 2X2 | 30000 | Tiles
663 |  | Adv for internal doors for Flat # 202,301 & 302 | 20000 | Wood
664 |  | Maipal Lifting Dust | 2500 | Flooring - Lifting
665 |  | Jagdamba Old Bal | 35000 | Misc
666 |  | Rethi for Coloumns & Tiles Fixing | 27000 | Sand
667 |  | MISC Expenses by Supervisor | 750 | Misc
668 | 7/11/20145 | AP Traders Balance | 20000 | Electrical Material
669 | 2015-11-07 | Essess Taps Payment for 101 & 102 | 45000 | Sanitory
670 | 2015-11-07 | Marble Fixer for 201 | 4000 | flooring - Marble
671 | 2015-11-07 | rethi Lifting for Flooring | 3500 | flooring - Lifting
672 | 2015-11-11 | Dust Lifting for Flooring | 3100 | flooring - Lifting
673 | 2015-11-11 | Marble & granite for 201 | 3500 | flooring - Marble
674 | 2015-11-11 | Supervisor MISC | 500 | Misc
675 | 2015-11-11 | Marble Payment for 201 | 15000 | flooring - Marble
676 | 2015-11-11 | Tiles Fixer Munaaf Bh | 5000 | Tiles Fixer
677 | 2015-11-11 | MISC Labour | 500 | Misc
678 | 2015-11-14 | Electrition Payment Sultan Bh | 5000 | Electrition
679 | 2015-11-14 | Dust and Kankar | 13000 | Kankar
680 | 2015-11-14 | Kankar Lifting | 4500 | Kankar
681 | 2015-11-14 | Marble Fixer for 201 | 9000 | flooring - Marble
682 | 2015-11-14 | Electriccal Final Fitting Material | 20100 | Electrical Material
683 | 2015-11-14 | White Cement MISC | 260 | Misc
684 | 2015-11-14 | Water Conn Labour | 1600 | Aminities - Water Dept
685 | 2015-11-14 | Marble Fixer 2K Bal | 7000 | flooring - Marble
686 | 2015-11-14 | Imran Painter | 2000 | Painter
687 | 2015-11-14 | Water DD | 56700 | Aminities - Water Dept
688 | 2015-11-14 | Marble Bal Paid for Flat 201 | 13000 | flooring - Marble
689 | 2014-11-14 | MISC Exp by Sup | 300 | Misc
690 | 2015-11-16 | Steel for Columns for 5th Floor | 28750 | Steel
691 | 2015-11-16 | MISC Exp | 250 | Misc
692 | 2015-11-17 | Sanitory for 1st Flr MISC | 4590 | Plumbing Material
693 | 2015-11-17 | Supervisor Advance | 4100 | UVI
694 | 2015-11-20 | Polish Stone for Parking | 11500 | Aminities - Parking Flooring
695 | 2015-11-20 | Munaaf Bh | 5000 | Tiles Fixer
696 | 2015-11-20 | False Ceiling | 5000 | False Ceiling
697 | 2015-11-20 | Parking Stones Fixer (Chand Pasha) | 4500 | Aminities - Parking Flooring
698 | 2015-11-20 | Carpenter Chary | 1400 | Wood
699 | 2015-11-20 | Chipping Labour | 2000 | Chipping
700 | 2015-11-20 | MISC Exp | 2000 | Misc
701 | 2015-11-20 | MISC Labour | 470 | Misc
702 | 2015-11-20 | Gowa Fixing | 3000 | Aminities - Gowa
703 | 2015-11-20 | Gowa Lakdi | 10000 | Aminities - Gowa
704 | 2015-11-20 | Groute for Flooring | 250 | flooring - Marble
705 | 2015-11-25 | Centering Payment | 40000 | Centering
706 | 2015-11-25 | Chipping | 3000 | Chipping
707 | 2015-11-25 | Painter Imran Payment | 5000 | Painter
708 | 2015-11-25 | Door Polish | 5000 | wood
709 | 2015-11-25 | Water Connection Payment | 20000 | Aminities - Water Dept
710 | 2015-11-28 | MISC ExP | 300 | Misc
711 | 2015-11-28 | Oil | 350 | Misc
712 | 2015-11-28 | Elec Bill | 2227 | Utilities
713 | 2015-11-28 | MISC Documentation | 200 | Misc
714 | 2015-11-28 | Dust Lifting for Flooring | 1400 | flooring - Lifting
715 | 2015-11-28 | Paint Material | 5050 | Painter Material
716 | 2015-11-28 | Parking Sone | 2000 | Aminities - Parking Flooring
717 | 2015-11-28 | Watchman Room Concreting Labour | 2000 | Misc
718 | 2015-11-28 | Kankar | 6000 | Kankar
719 | 2015-11-28 | Plumbing Material | 4000 | Plumbing Material
720 | 2015-11-28 | Painter Payment | 5000 | Painter
721 | 2015-11-28 | Gowa Payment | 4000 | Aminities - Gowa
722 | 2015-11-30 | Chiiping Slab | 2000 | Chipping
723 | 2015-11-30 | Tiles for Basin Area | 1500 | Tiles
724 | 2015-11-30 | BPS Payment | 10000 | Aminities - GHMC
725 | 2012-12-03 | BPS Payment as DD | 10000 | Aminities - GHMC
726 | 2015-12-04 | Railing ADV Azghar | 5000 | Aminities - Fabrication
727 | 2015-12-04 | Nageshwar for Brick Work | 50000 | Mason - Brick
728 | 2015-12-04 | Patta for Gowa | 5000 | Aminities - Gowa
729 | 2015-12-04 | Watchman Salary | 6000 | Utilities
730 | 2015-12-04 | Supervisor Salary | 6900 | UVI
731 | 2015-12-04 | Munaaf Bh Tiles Fixer | 30000 | Tiles Fixer
732 | 2015-12-04 | Gowa Raju | 2000 | Aminities - Gowa
733 | 2015-12-04 | Nageshwar Payment Under Dept | 7600 | Mason - Dept
734 | 2015-12-04 | MISC Exp | 500 | Misc
735 | 2015-12-04 | Parking Stones Fixer (Chand Pasha) | 3000 | Aminities - Parking Flooring
736 | 2015-12-04 | Security Room Door & Frame | 3000 | Wood
737 | 2015-12-05 | Brick for Security Room | 3000 | Brick
738 | 2015-12-05 | Sand for Brick 7 Plastering Work | 11000 | Sand
739 | 2015-12-06 | Mainhole Brick for Security Room | 5500 | Brick
740 | 2015-12-06 | Ultra Tech Block for Stircase case work | 8600 | Brick
741 | 2015-12-06 | Water Connection Ashfaq Bh | 5000 | Aminities - Water Dept
742 | 2015-12-06 | MISC Labour | 1300 | Misc
743 | 2015-12-06 | Gowa | 8000 | Aminities - Gowa
744 | 2015-12-06 | Plumbers - Watchman Bathroom + Chambers + Other Extra Works | 12000 | Plumber
745 | 2015-12-07 | Summersible Pump for Sump | 13300 | Aminities - Borewell
746 | 2015-12-07 | MISC Exp | 300 | Misc
747 | 2015-12-07 | Fabricator Azghar for Railing | 10000 | Aminities - Fabrication
748 | 2015-12-08 | Painter Imran | 5000 | Painter
749 | 2015-12-08 | Ismail Bh | 3500 | Aminities - Parking Flooring
750 | 2015-12-08 | Centering | 1000 | Centering
751 | 2015-12-08 | Slab Joint Chemical | 5760 | Misc
752 | 2015-12-12 | DD for Transfarmer | 151000 | Aminities - Electrical Dept
753 | 2015-12-12 | Bakra & Others | 8000 | UVI
754 | 2015-12-12 | Painter Payment | 5000 | Painter
755 | 2015-12-12 | Granite for Parking Tiles | 1740 | Aminities - Parking Flooring
756 | 2015-12-12 | Granite for Parking Silver Grey | 7500 | Aminities - Parking Flooring
757 | 2015-12-12 | Painter Material | 710 | Painter Material
758 | 2015-12-12 | Munaaf Bh | 1800 | Tiles Fixer
759 | 2015-12-12 | MISC Labour | 500 | Misc
760 | 2015-12-12 | Concrere Labour Charges | 2500 | Misc
761 | 2015-12-12 | Mainholw Frames | 1350 | Misc
762 | 2015-12-12 | Nageshwar For Brick Work | 30000 | Mason - Brick
763 | 2015-12-12 | Nageshwar Dept | 900 | Mason - Dept
764 | 2015-12-12 | Nageshwar Dept | 5400 | Mason - Dept
765 | 2015-12-12 | Ismail Bh for Parking | 10000 | Aminities - Parking Flooring
766 | 2015-12-14 | Cement | 20000 | Cement
767 | 2015-12-14 | Parking Stone | 10000 | Aminities - Parking Flooring
768 | 2015-12-15 | Glass MISC Work | 300 | Misc
769 | 2015-12-15 | Indian Online Ads Login | 1900 | UVI
770 | 2015-12-15 | Fabricator Azghar for Railing | 20000 | Aminities - Fabrication
771 | 2015-12-15 | Transfarmer Srinivas | 50000 | Aminities - Electrical Dept
772 | 2015-12-15 | Generator Cable | 9000 | Aminities - Gen
773 | 2015-12-15 | Concrete Labour | 1600 | Misc
774 | 2015-12-15 | Tiles Payment | 4000 | Tiles
775 | 2015-12-15 | Dust for Flooring | 3200 | Sand
776 | 2015-12-15 | Centering Payment | 15000 | Centering
777 | 2015-12-15 | 101 & 102 Doors Polish | 3000 | Wood
778 | 2015-12-15 | Chipping Extra Balcony | 2000 | Chipping
779 | 2015-12-19 | Painter Payment | 4000 | Painter
780 | 2015-12-19 | Mason Payment | 9000 | Mason - Dept
781 | 2015-12-19 | Parking Work Payment Ismail Bh | 4000 | Aminities - Parking Flooring
782 | 2015-12-19 | Doors Hardware for 301 | 13040 | wood
783 | 2015-12-23 | Fabricator Azghar for Railing | 20000 | Aminities - Fabrication
784 | 2015-12-23 | Centering Payment to Azeem | 20000 | Centering
785 | 2015-12-23 | Concrete Labour for coloumns | 7500 | Misc
786 | 2015-12-23 | Paint Material | 5500 | Painter Material
787 | 2015-12-23 | MISC Doors Hardware | 1000 | wood
788 | 2015-12-23 | Carpenter Payment for Doors | 4230 | wood
789 | 2015-12-23 | False Ceiling Payment | 8000 | False Ceiling
790 | 2015-12-23 | Supervisor salary 14+1 Adv | 15000 | UVI
791 | 2015-12-23 | Labour for cleaning | 800 | MISC
792 | 2015-12-23 | Labour for concreting | 500 | MISC
793 | 2015-12-23 | Granite for parking | 1620 | Aminities - Parking Flooring
794 | 2015-12-23 | Watchman Salary ADV | 2000 | Utilities
795 | 2015-12-23 | MISC by Supervisor | 300 | Misc
796 | 2015-12-29 | Electricity Bill | 2900 | Utilities
797 | 2015-12-29 | Centering Payment | 20000 | Centering
798 | 2015-12-29 | Gowa Labour | 1000 | Aminities - Gowa
799 | 2015-12-29 | Chipping | 1000 | Chipping
800 | 2015-12-29 | Steel for 5th Flr Slab | 215000 | Steel
801 | 2015-12-29 | Cement 400 Bags Chttinad 53 | 140500 | Cement
802 | 2015-12-30 | Bending Wire & Oil | 3000 | Steel
803 | 2015-12-30 | Extra Beam Rings | 1630 | Steel
804 | 2015-12-30 | Watchman Salary | 5000 | Utilities
805 | 2015-12-30 | MISC by Supervisor | 300 | Misc
806 | 2015-12-30 | Electrical Material for Slab | 9500 | Electrical Material
807 | 2016-01-01 | Transfarmer Srinivas | 20000 | Aminities - Electrical Dept
808 | 2016-01-01 | Mainhole Frames | 2310 | Plumbing Material
809 | 2016-01-01 | Centering Food - Dinner | 2000 | Misc
810 | 2016-01-01 | MISC by Supervisor | 750 | Misc
811 | 2016-01-03 | Centering Payment | 25000 | Centering
812 | 2016-01-03 | Mason Payment | 40000 | Mason - Concrete
813 | 2016-01-03 | Kankar for slab | 30000 | Kankar
814 | 2016-01-03 | Sand for 5th Floor Slan @ 11.70 per ton | 57200 | Sand
815 | 2016-01-03 | Light for night work | 1650 | Misc
816 | 2015-01-03 | Electrition Payment for Slab work | 4000 | Electrition
817 | 2015-01-03 | Unknown | 2000 | Misc
818 | 2015-01-03 | Tips on Slab day Cent+W.Man+Labour+Mason | 2600 | Misc
819 | 2015-01-03 | Water Bill | 2100 | Utilities
820 | 2016-01-05 | Electricity Bill | 2900 | Utilities
821 | 2015-01-03 | Mason Payment - Brick work Bal | 7350 | Mason - Brick
822 | 2016-01-06 | Watchman Adv | 500 | Utilities
823 | 2015-01-03 | Centering Payment | 25000 | Centering
824 | 2016-01-08 | Concrete for final coloumns | 5000 | Mason - Concrete
825 | 2016-01-03 | Paint Material | 2400 | Painter Material
826 | 2016-01-09 | Door Fitting Adv for Flats | 5000 | Wood
827 | 2016-01-12 | Doors Payment for 301 | 6500 | Wood
828 | 2016-01-12 | Fabrication for Railing (Bal 3K) | 10000 | Aminities - Fabrication
829 | 2016-01-12 | Ismail Bh for Parking | 3000 | Aminities - Parking Flooring
830 | 2016-01-12 | Doors for Flat # 201,202,302,401 & 402 - Adv to A.Mannan | 10000 | Wood
831 | 2016-01-01 | GPA & Courier | 1800 | Aminities - Documentation
832 | 2016-01-14 | Security Room Slab & Water Tank Slab Concrete | 5000 | Mason - Concrete
833 | 2016-01-14 | Chemical for Water Tank Base | 500 | Misc
834 | 2016-01-13 | Chipping for Final Slab | 1000 | Chipping
835 | 2016-01-13 | Centering Payment | 30000 | Centering
836 | 2016-01-01 | Mason Brick {ayment Added from HH Project | 30000 | Mason - Brick
837 | 2016-01-19 | Centering Payment | 30000 | Centering
838 | 2016-01-19 | MISC by Supervisor | 1000 | MISC
839 | 2016-01-19 | 2nd Lift Payment | 100000 | Aminities - Lift
840 | 2016-01-19 | Mujahed Bh Floor Plan for 501 & 601 | 4000 | Aminities - Designing
841 | 2016-01-19 | MISC Hardware from Sai Krishna | 14000 | MISC
842 | 2016-01-19 | Flat # 301 Commission | 30000 | UVI
843 | 2016-01-20 | Sand for Slab & water Tank | 20300 | Sand
844 | 2016-01-22 | Mason Bal Brick Work Payment Upto 4th Flr | 40000 | Mason - Brick
845 | 2016-01-22 | MISC by Supervisor | 500 | MISC
846 | 2016-01-23 | Doors Bal for 201,202,301,302,401,402 | 40000 | Wood
847 | 2016-01-23 | MISC Labour | 700 | MISC
848 | 2016-01-23 | Concrete Labour for water Tank | 3200 | Mason - Concrete
849 | 2016-01-23 | Watchman Adv | 500 | Utilities
850 | 2016-01-23 | Chipping | 1000 | Chipping
851 | 2016-01-23 | MISC Hardware from Sai Krishna | 500 | MISC
852 | 2016-01-24 | Door Frames for 5 & 6th Flr | 50000 | Wood
853 | 2016-01-24 | Hinges for Doors | 6000 | Wood
854 | 2016-01-24 | Electrical Material for Final Slab | 8000 | Electrical Material
855 | 2016-01-27 | Doors Polish Adv for 201,202,301,302 | 10000 | Wood
856 | 2016-01-27 | Steel for Final Slab & Water Tank Steel | 150000 | Steel
857 | 2016-01-27 | Ultra tech Brick for 5 & 6th Flr & Checmical | 125000 | Brick
858 | 2016-01-27 | False Ceiling final Payment upto 4th Flr | 8000 | False Ceiling
859 | 2016-01-27 | Centrering Payment | 20000 | Centering
860 | 2016-01-27 | Elec Bill | 3820 | Utilities
861 | 2016-01-27 | Red Brick for 9" Wall | 18000 | Brick
862 | 2016-01-27 | Saber Bh for Doors Fitting 301,302,201,202 to A.Samad | 7000 | Wood
863 | 2016-01-27 | Electricals Lights for Flats & Common Area ( Panel Fittings & COB) | 35350 | Electrical Material
864 | 2016-01-28 | Fabrication Adv for Elevation Railing | 10000 | Aminities - Fabrication
865 | 2016-01-29 | Concrete Payment for Final Slab | 30000 | Mason - Concrete
866 | 2016-01-29 | Centering Payment on Final Slab day | 30000 | Centering
867 | 2016-01-29 | Electrition Payment for Final Slab Work | 4000 | Electrition
868 | 2016-01-29 | Sand for Final Slab | 42000 | Sand
869 | 2016-01-29 | Kankar for Final Slab | 18000 | Kankar
870 | 2016-01-30 | Transfarmer Final Payment | 24000 | Aminities - Electrical Dept
871 | 2016-01-30 | Frames Final Payment for 5 & 6 Flr | 23000 | Wood
872 | 2016-01-31 | Gowa Tieing Adv | 1000 | Aminities - Gowa
873 | 2016-02-02 | Watchman Salary | 6000 | Utilities
874 | 2016-02-02 | Centering Payment | 20000 | Centering
875 | 2016-02-04 | MISC by Supervisor | 1000 | MISC
876 | 2016-02-04 | Plumbing Material for terrace Fittings | 70000 | Plumbing Material
877 | 2016-02-04 | Gowa Lakdi | 7500 | Aminities - Gowa
878 | 2016-02-04 | MISC Exp | 400 | MISC
879 | 2016-02-04 | Gowa patta | 1500 | Aminities - Gowa
880 | 2016-02-04 | Teak Frames Transport | 1500 | Wood
881 | 2016-02-04 | MISC by Supervisor | 300 | MISC
882 | 2016-02-06 | Mason Payment - Brick work | 9150 | Mason - Brick
883 | 2016-02-06 | Elec Payment | 5000 | Electrition
884 | 2016-02-06 | Gowa Tieing Labour @ Garden site & Elevation Site | 11000 | Aminities - Gowa
885 | 2016-02-06 | Chipping | 4500 | Chipping
886 | 2016-02-06 | Doors Hardware for 302 & 202 | 15000 | Wood
887 | 2016-02-06 | Lal mithi for Duplex Staircase | 6000 | Sand
888 | 2016-02-06 | Painter Payment | 7000 | Painter
889 | 2016-02-06 | Lifting Labour for Sand | 4500 | Mason - Lift
890 | 2016-02-05 | Tarpaulin | 1000 | Aminities - Gowa
891 | 2016-02-06 | Checmical for Water Tank & Slab | 2700 | Water Proofing
892 | 2016-02-06 | Electrical Material for Lift | 9000 | Aminities - Lift
893 | 2016-02-06 | Paint for Flat # 301 | 7000 | Painter Material
894 | 2016-02-11 | Electrical Wires | 11000 | Electrical Material
895 | 2016-02-11 | MISC Hardware from Sai Krishna | 15000 | MISC
896 | 2016-02-11 | Elevation Railing Payment | 10000 | Aminities - Fabrication
897 | 2016-02-11 | 3rd Lift Payment | 100000 | Aminities - Lift
898 | 2016-02-11 | Mason Adv for Brick Work for 5 & 6th Flr | 30000 | Mason - Brick
899 | 2016-02-12 | Taufeeq Elevation redesigh | 5000 | Aminities - Designing
900 | 2016-02-12 | Qasim Plumber | 2500 | Plumber
901 | 2016-02-12 | Mason Payment for Brick | 23000 | Mason - Brick
902 | 2016-02-12 | Centering Payment | 20000 | Centering
903 | 2016-02-13 | Taanchay for Final slab | 1800 | Chipping
904 | 2016-02-13 | Chipping | 3000 | Chipping
905 | 2016-02-13 | Door Polish | 17000 | Wood
906 | 2016-02-13 | Painter Payment | 5500 | Painter
907 | 2016-02-13 | Lifting red sand | 2700 | Mason - Lift
908 | 2016-02-13 | Lift white wash - Labour | 1500 | Painter
909 | 2016-02-13 | Sand for plastering | 33000 | Sand
910 | 2016-02-14 | Fabrication for Railing | 5000 | Aminities - Fabrication
911 | 2016-02-14 | watchman adv salary | 1000 | Utilities
912 | 2016-02-16 | additional chemical bags | 7500 | Cement
913 | 2016-02-16 | additional Red bricks | 18400 | Brick
914 | 2016-02-17 | Internet & Phone Bill (UVI) | 2000 | UVI
915 | 2016-02-17 | Mics Exp | 300 | MISC
916 | 2016-02-20 | additional bricks | 5400 | Brick
917 | 2016-02-20 | Mason Payment Brick Work | 17000 | Mason - Brick
918 | 2016-02-20 | Granite Fixer alUddin | 2000 | Granite Fixer
919 | 2016-02-22 | MISC Labour | 300 | MISC
920 | 2016-02-22 | Sand Lifting | 3000 | Mason - Lift
921 | 2016-02-24 | Red Brick for 9" Wall | 18000 | Brick
922 | 2016-02-23 | Sanitory Adv for 301 | 10000 | Sanitory
923 | 2016-02-27 | Door Polish (Kamal Bh 2K Bal) | 3000 | Polish
924 | 2016-02-27 | Centering Payment | 14000 | Centering
925 | 2016-02-27 | Mason Payment - Brick | 15000 | Mason - Brick
926 | 2016-02-27 | Lifting Payment Brick | 5200 | Mason - Lift
927 | 2016-02-27 | Lifting Payment Brick | 6500 | Mason - Lift
928 | 2016-02-27 | Fabrication MISC - Sump, Covers, sidi & others | 10000 | Aminities - Fabrication
929 | 2016-02-27 | Steeil & cement | 50000 | Steel
930 | 2016-02-27 | MISC Labour | 1500 | MISC
931 | 2016-02-27 | Plumbing Material for 301 | 11200 | Plumbing Material
932 | 2016-02-27 | Plumber Payment for terrace fittings | 7500 | Plumber
933 | 2016-02-27 | Sanitory bal for 301 | 70000 | Sanitory
934 | 2016-02-27 | Paint MISC | 520 | Painter Material
935 | 2016-02-24 | Plumbing MISC Material | 800 | Plumbing Material
936 | 2016-02-28 | Additional Brick 4" & 8" ultra tech | 10750 | Brick
937 | 2016-03-03 | Watchman Salary | 5000 | Utilities
938 | 2016-03-03 | Elec Bill | 4200 | Utilities
939 | 2016-03-03 | MISC by Supervisor | 230 | MISC
940 | 2016-03-03 | Opening Lift Gowa Labour | 500 | Aminities - Gowa
941 | 2016-03-03 | Sultan Bh Elec Bal Payment | 24000 | Electrition
942 | 2016-03-05 | Chipping | 1000 | Chipping
943 | 2016-03-05 | Cera Fittings for 202 & 302 | 35000 | Sanitory
944 | 2016-03-06 | Mason Payment | 9000 | Mason - Brick
945 | 2016-03-06 | MISC by Supervisor | 300 | MISC
946 | 2016-03-06 | MISC Labour | 500 | MISC
947 | 2016-03-06 | Tiles Fixer for Basin area @ 202 & 302 | 500 | Tiles Fixer
948 | 2016-03-06 | 4th Payment for Lift | 75000 | Aminities - Lift
949 | 2016-03-06 | Final Payment for 202 & 302 - Omer Traders | 7000 | Painter Material
950 | 2016-03-06 | Additional Brick for Elevation | 28800 | Brick
951 | 2016-03-06 | Chemical for Tiles @ Basin Area | 1500 | Tiles
952 | 2016-03-06 | Tiles for Basin Area |  | Tiles
953 | 2016-03-06 | Sanitary for 202 & 302 CP Fittings Ess Ess | 42016 | Sanitory
954 | 2016-03-11 | Electricals for Common area & 202 & 302 | 10600 | Electrical Material
955 | 2016-03-11 | Painter Payment | 7000 | Painter
956 | 2016-03-12 | Mason Payment | 20000 | Mason - Brick
957 | 2016-03-12 | MISC Paint Material | 750 | Painter Material
958 | 2016-03-14 | Additional Bricks | 25000 | Brick
959 | 2016-03-15 | Centering Payment for Chajja 501,502,601 & 602 ( Bal ?) | 10000 | Centering
960 | 2016-03-15 | GHMC BRB | 15000 | Aminities - GHMC
961 | 2016-03-15 | MISC by Supervisor | 2000 | MISC
962 | 2016-03-19 | Mason Payment | 7000 | Mason - Brick
| 2016-03-19 | Painter Payment | 5000 | Painter
| 2016-03-19 | Paint Material | 10000 | Paint Material
| 2016-03-19 | Transfarmet Moved (15k Bal) | 20000 | Aminities - Electrical Dept
| 2016-03-16 | Grills from Zaib Gulshan - Transport | 500 | Misc
| 2016-03-16 | MISC by Supervisor | 500 | Misc
| 2016-03-16 | Gowa Lakdi | 7450 | Aminities - Gowa
| 2016-03-16 | Additional Bricks | 2200 | Brick
| 2016-03-16 | Gowa Rassi | 1080 | Aminities - Gowa
| 2016-03-16 | Gowa Labour | 3500 | Aminities - Gowa
| 2016-03-16 | Tadkay | 4150 | Aminities - Gowa
| 2016-03-16 | Safety Belts | 700 | MISC
| 2016-03-16 | Mics Paint Material | 1040 | Paint Material
| 2016-03-16 | Watchman Adv | 200 | Utilities
| 2016-03-16 | Superviser Adv - Rizwan Bh | 5000 | UVI
| 2016-03-18 | Sand for Outer Plastering | 34000 | Sand
| 2016-03-18 | Plumber Payment for 5 & 6th Flr | 20000 | Plumber
| 2016-03-19 | Paint Material | 5000 | Paint Material
| 2016-03-19 | Janta Paste & Misc | 500 | MISC
| 2016-03-26 | Painter Payment | 7000 | Painter
| 2016-03-26 | Mason Payment | 23000 | Mason - Brick
| 2016-03-26 | Mason Payment - Lifting | 14000 | Mason - Brick
| 2016-03-26 | Dust for Flooring | 4000 | Flooring - Lifting
| 2016-03-26 | Doors HW for 201 | 11200 | Wood
| 2016-03-26 | Paint Material | 5000 | Paint Material
| 2016-03-28 | Water Proofing Adv for Water Tanks to Qasim | 6000 | Water Proofing
| 2016-03-28 | Elec Bill | 4400 | Utilities
| 2016-03-28 | Gowa Misc Work | 1500 | Aminities - Gowa
|  | Dust for Flooring | 7000 | Flooring - Lifting
|  | Granite for Staircase 5 & 6th | 3000 | Aminities - Parking Flooring
|  | Plumbing Materila for 5 & 6th Floor (Internal) | 47300 | Plumbing Material
|  | Hardware for doors for 202 & 302 | 18500 | Wood
|  | UPVC Balance Payment for 301,302,401 & 402 | 44000 | UPVC
|  | Ismail bh for Polish | 3000 | Flooring - Marble
| 2016-04-02 | Transfarmer Moved | 10000 | Aminities - Electrical Dept
| 2016-03-20 | Cement Bags | 60000 | Cement
| 2016-04-02 | Mason Payment for Brick Work (6K Bal) | 21000 | Mason - Brick
| 2016-04-02 | Dust Lifting for Flooring | 4000 | Flooring - Lifting
| 2016-04-01 | Supervisor salary (Rizwan Bh) | 7000 | UVI
| 2016-04-01 | Watchman Salary (Ramlu) | 5800 | Utilities
| 2016-04-01 | Azghar Fabricator | 4000 | Aminities - Fabrication
| 2016-04-01 | Imran Painter | 15000 | Painter
| 2016-04-02 | Chipping @ elevation site | 2000 | Chipping
| 2016-04-02 | Ismail Bh for 202 Polish | 3000 | Marble
| 2016-04-02 | Additional Bricks Bal Paid | 4000 | Brick
| 2016-04-04 | Plumbing Misc items | 1000 | Plumbing Material
| 2016-04-05 | Water Proofing for Water Tank Bal | 5000 | Water Proofing
| 2016-04-05 | Plumbing Payment | 6000 | Plumber
| 2016-04-05 | Electrical Material for 5th & 6th Floor | 12000 | Electrical Material
| 2016-04-05 | Misc Plumbing Material (Jaguar outer Part and jets) | 10000 | Plumbing Material
| 2016-04-05 | Cement Bags | 45000 | Cement
| 2016-04-05 | Sand for Plastering | 32500 | Sand
| 2016-04-05 | Balance payment for Chajjay steel & cement | 25000 | Steel
Total Amount Spent On RC Till 29-Oct-2014 |  |  | 16521576